## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Student | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail /OTP
1 | SB1/US2 | Student | Receive A Confirmation Mail/OTP | I Can Access The Assesment portal
1 | SB1/US3 | Student | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile
1 | SB1/US4 | Student | View The Subject Detalis | I Can See The Marking Scheme
1 | SB1/US5 | Student | View The Topic details of particular subject | I Can give exam according to the subject
1 | SB1/US6 | Student | Modify The Account Password | I Can Keep My Account Secure
1 | SB1/US7 | Student | Give Feedback/Suggestions | The Way Of Working Of Application Can Be Improved
1 | SB1/US8 | Student | give the exam | register user can give the exam
1 | SB1/US9 | Student | select the subjet for the exam | user can select the subject for the exam
1 | SB1/US10 | Student | View My Result | I Can Analyze My Performance
1 | SB1/US11 | Student | Discuss Among Other Students | I Can Share My Experience
DATABASE
2 | SB2/US12 | DBA | create database | create database for application
2 | SB2/US13 | DBA | create tables | Create tables for the database
2 | SB2/US14 | DBA | create connectivity with database | connectivity with database
2 | SB2/US15 | DBA | fire the queries | fire the query
2 | SB2/US16 | DBA | Fire Insert Queries | I Can Insert New Records In The Database
2 | SB2/US17 | DBA | Fire Select Queries | I Can View The Records
2 | SB2/US18 | DBA | Fire Update Queries | I Can Keep The Database Updated
2 | SB2/US19 | DBA | Fire Delete Queries | I Can Remove Unwanted questions
2 | SB2/US20 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use
2 | SB2/US21 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More
ADMIN
3 | SB3/US22 | ADMIN | Login Into The System Using Mail Id And Password | I Can Access The Assesment Portal
3 | SB3/US23 | ADMIN | Modify The Account Password | I Can Keep My Account Secure
3 | SB3/US24 | ADMIN | Finalize The Subjects For Test | Test Allotment Subject Can Be Done
3 | SB3/US25 | ADMIN | Add The Questions | Add the Question Of all Subjects
3 | SB3/US26 | ADMIN | Allot The Subjects to be Test | Decide the subject to Test
3 | SB3/US27 | ADMIN | Add some notes about the topic | some idea about about the topic
3 | SB3/US28 | ADMIN | View The Result List Of The Students | I Can Monitor The Performance Of The Students
3 | SB3/US29 | ADMIN | Handle complete data of user | I handle complete data of user
4 | SB4/US30 | ADMIN | handle the complete database | I handle the complete database
4 | SB4/US31 | ADMIN | Upload Excel Sheet of questions | I can upload excel sheet of question
4 | SB4/US32 | ADMIN | edit the marks of question | I can edit the marks of the question
4 | SB4/US33 | ADMIN | provide a negative marking | I can provide negative marking
4 | SB4/US34 | ADMIN | manage result | I can manage the result
4 | SB4/US35 | ADMIN | manage questions | I can manage the question
4 | SB4/US36 | ADMIN | manage the answers of the question | I can manage the answer of the question
4 | SB4/US37 | ADMIN | provide the facility to choose the sector of exam | I can provide the facility to choose the sector of the exam
4 | SB4/US38 | ADMIN | handle the user request for forget password | I can handle the user forget password
4 | SB4/US39 | ADMIN | update the password in database | I can update the password in database
4 | SB4/US40 | ADMIN | Add the questions | I can add the questions
4 | SB4/US41 | ADMIN | add new subject for test | I can add new subject for test
4 | SB4/US42 | ADMIN | add answer of the questions | I can add answer of the question

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Assessment Portal>
SB1/US1 | Registration | SB1/D1/T1 | firstly we make signup page using android in xml file | PS | COMPLETED | 23-09-2018
|  | SB1/D1/T2 | use validation in sign up page | SJ | COMPLETED | 23-09-2018
|  | SB1/D1/T3 | write code for sign up page in java | PS+SJ | COMPLETED | 23-09-2018
|  | SB1/D1/T4 | create connectivity with database using php | PS+RK | COMPLETED | 23-09-2018
|  | SB1/D1/T5 | create database for store the data | RK | COMPLETED | 23-09-2018
|  | SB1/D1/T6 | fire the insert query for store data | SJ+RK | COMPLETED | 23-09-2018
SB1/US2 | Registration verification | SB1/D2/T1 | use material design In registration page | SJ | COMPLETED | 23-09-2018
|  | SB1/D2/T2 |  | PS+SJ | COMPLETED | 23-09-2018
|  | SB1/D2/T3 | there is pop-up for success completion |  | COMPLETED
|  | SB1/D2/T4 | Email for verification write code in java file |  | COMPLETED
|  | SB1/D2/T5 |  |  | COMPLETED
SB1/US3 | Login | SB1/D3/T1 | we make login page using android inXml file | PS | COMPLETED | 26-09-2018
|  | SB1/D3/T2 | use validation in Login page | SJ | COMPLETED | 26-09-2018
|  | SB1/D3/T3 | fire the insert query for store data | PS+SJ | COMPLETED | 26-09-2018
|  | SB1/D3/T4 | fire the select query for store data | PS+RK | COMPLETED | 26-09-2018
SB1/US6 | Forget Password | SB1/D4/T1 | using android we code for forget password | RK | COMPLETED
|  | SB1/D4/T2 |  |  | COMPLETED
|  | SB1/D4/T3 |  |  | COMPLETED
|  | SB1/D4/T4 |  |  | COMPLETED
|  | SB1/D4/T5 |  |  | COMPLETED | 26-09-2018
SB1/US7 | Modify account | SB1/D5/T1 | we create some edit link to edit an account | SJ | COMPLETED | 26-09-2018
|  | SB1/D5/T2 | we make forget password to modify account | PS+SJ | COMPLETED
SB1/D5/T3
SB1/D5/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup |  |  | completed
|  | Search about components required |  |  | completed
|  | Purchase component from Market |  |  | completed
|  | Develop the hardware |  |  | completed
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application |  |  | completed
|  | search paint application |  |  | completed
|  | search video making application |  |  | completed
|  | search audio recording applications |  |  | completed
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials |  |  | completed
|  | Study tutorials |  |  | completed
|  | start with Basics of c# |  |  | completed
|  | start with Basics of c# |  |  | completed
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c# |  |  | completed
|  | start with Basics of c# |  |  | completed
|  | coding of onscreen application |  |  | completed | 0
|  | coding of onscreen application |  |  | completed | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  | completed | 0
|  | coding of onscreen application |  |  | completed | 0
|  | Debug the code |  |  | completed
|  | Debug the code |  |  | completed
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen |  |  | completed
|  | Interface it with PC/laptop |  |  | completed
|  | Switch on the projector and set the projected screen |  |  | completed
|  | Interface it with PC/laptop |  |  | completed
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen |  |  | completed
|  | Use different applications on the virtual screen |  |  | completed
|  | Check the changes made at the virtual screen |  |  | completed
|  | Checking if it is working effectively with the laptop and not damaged |  |  | completed
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables |  |  | completed
|  | Prepare all software deliverables |  |  | completed
|  | Prepare a hardware & software guide |  |  | completed
|  | Prepare a user manual & guide for the users |  |  | completed
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project |  |  | completed
|  | Project demonstration |  |  | completed
|  | Project demonstration |  |  | completed
|  | Project to be operated by different users |  |  | completed
| PS | Pankaj Sharma
| RK | Ravi Kumawat
| SJ | Sunil Jangid
Verified By:
MR. Praveen Gupta

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 15 | 15 | Tasks
2018-09-12 | 11 | 12
2018-09-11 | 7 | 8
2018-09-14 | 4 | 6
2018-09-16 | 2 | 3
2018-09-18 | 0 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Assessment Portal>
SB2/US1 | Add user | SB2/D1/T1 | Designing the GUI | PS | COMPLETED | 2018-10-10
|  | SB2/D1/T2 | Connection with database to fetch the data | RK | COMPLETED | 2018-10-10
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RK+PS+SJ | COMPLETED | 2018-10-10
SB2/US2 | Register student | SB2/D2/T1 | Designing of GUI | SJ | COMPLETED | 2018-10-10
|  | SB2/D2/T2 | Validating user input at client level | RK | COMPLETED | 2018-10-10
|  | SB2/D2/T3 | Validating user input at server level | SJ | COMPLETED | 2018-10-10
|  | SB2/D2/T4 | Connection with Database to insert the record. | PS | COMPLETED | 2018-10-10
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RK+PS+SJ | COMPLETED | 2018-10-10
SB2/US3 | Exam | SB1/D6/T1 | selection of exam provided to select | RK | COMPLETED | 2018-10-10
|  | SB1/D6/T2 | we make layout to select subject | RK | COMPLETED | 2018-10-10
|  | SB1/D6/T3 |  |  | COMPLETED
|  | SB1/D6/T4 |  |  | COMPLETED
|  | SB1/D6/T5 |  |  | COMPLETED
SB2/US4 | Question | SB1/D7/T2 | here we use check box to select the option | SJ | COMPLETED | 26/10/2018
|  | SB1/D7/T3 | here is skip and next or submit button | SJ | COMPLETED | 26/10/2018
|  | SB1/D7/T4 |  |  | COMPLETED
|  | SB1/D7/T5 |  |  | COMPLETED
SB2/US5 | Result | SB1/D8/T1 | after exam user fatch the the result from the database | PS+RK | COMPLETED | 26/10/2018
|  | SB1/D8/T2 | user use select query | PS+SJ | COMPLETED | 26/10/2018
|  | SB1/D8/T3 | first store using insert query | PS | COMPLETED | 26/10/2018
|  | SB1/D8/T4 |  |  | COMPLETED

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup |  |  | completed
|  | Search about components required |  |  | completed
|  | Purchase component from Market |  |  | completed
|  | Develop the hardware |  |  | completed
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application |  |  | completed
|  | search paint application |  |  | completed
|  | search video making application |  |  | completed
|  | search audio recording applications |  |  | completed
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials |  |  | completed
|  | Study tutorials |  |  | completed
|  | start with Basics of c# |  |  | completed
|  | start with Basics of c# |  |  | completed
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c# |  |  | completed
|  | start with Basics of c# |  |  | completed
|  | coding of onscreen application |  |  | completed | 0
|  | coding of onscreen application |  |  | completed | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  | completed | 0
|  | coding of onscreen application |  |  | completed | 0
|  | Debug the code |  |  | completed
|  | Debug the code |  |  | completed
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen |  |  | completed
|  | Interface it with PC/laptop |  |  | completed
|  | Switch on the projector and set the projected screen |  |  | completed
|  | Interface it with PC/laptop |  |  | completed
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen |  |  | completed
|  | Use different applications on the virtual screen |  |  | completed
|  | Check the changes made at the virtual screen |  |  | completed
|  | Checking if it is working effectively with the laptop and not damaged |  |  | completed
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables |  |  | completed
|  | Prepare all software deliverables |  |  | completed
|  | Prepare a hardware & software guide |  |  | completed
|  | Prepare a user manual & guide for the users |  |  | completed
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project |  |  | completed
|  | Project demonstration |  |  | completed
|  | Project demonstration |  |  | completed
|  | Project to be operated by different users |  |  | completed
| PS | Pankaj Sharma
| RK | Ravi Kumawat
| SJ | Sunil Jangid
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 15 | 15 | Tasks
2017-09-28 | 13 | 14
2017-10-02 | 11 | 12
2017-10-05 | 7 | 9
2017-10-07 | 3 | 5
2017-10-09 | 0 | 0
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Assessment Portal>
SB3/US1 | Login | SB1/D3/T1 | we make login page using android inXml file | PS | COMPLETED | 26-10-2018
|  | SB1/D3/T2 | use validation in Login page | PS+RK | COMPLETED | 26-10-2018
|  | SB1/D3/T3 | fire the insert query for store data | SJ+RK | COMPLETED | 26-10-2018
|  | SB1/D3/T4 | fire the select query for store data | SJ | COMPLETED | 26-10-2018
SB3/US2 | Forget password | SB1/D4/T1 | using android we code for forget password | PS+SJ | COMPLETED | 26-10-2018
SB1/D4/T2
SB1/D4/T3
SB1/D4/T4
SB3/US3 | Modify Account | SB1/D5/T1 | we create some edit link to edit an account | RK | COMPLETED | 26-10-2018
|  | SB1/D5/T2 | we make forget password to modify account | RK+SJ | COMPLETED | 26-10-2018
SB1/D5/T3
SB1/D5/T4
SB3/US4 | Exams | SB1/D6/T1 | create page for exams using layout | PS | COMPLETED | 26-10-2018
|  | SB1/D6/T2 | for every exam provide different button to click on that | PS+SJ | COMPLETED | 26-10-2018
SB1/D6/T3
SB1/D6/T4
SB3/US5 | Questions | SB1/D7/T2 | here we use check box to select the option | PS | COMPLETED | 26-10-2018
|  | SB1/D7/T3 | here is skip and next or submit button | PS+RK | COMPLETED | 26-10-2018
|  | SB1/D7/T4 | can upload excel for the questions | SJ+RK | COMPLETED | 26-10-2018
SB1/D7/T5
SB3/US6 | Result | SB1/D8/T1 | after exam user fatch the the result from the database | PS+RK+SJ | COMPLETED | 26-10-2018
|  | SB1/D8/T2 | user use select query | PS+RK | COMPLETED | 26-10-2018
|  | SB1/D8/T3 | first store using insert query | SJ+RK | COMPLETED | 26-10-2018
SB1/D8/T4
SB3/US7 | Add Subject | SB2/D6/T1 | Designing of GUI | PS | COMPLETED | 2018-03-11
|  | SB2/D6/T2 | Validating user input at client level | PS+RK | COMPLETED | 2018-03-11
|  | SB2/D6/T3 | Validating user input at server level | SJ+RK | COMPLETED | 2018-03-11
|  | SB2/D6/T4 | Connection with Database to insert the record. | SJ | COMPLETED | 2018-03-11
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | PS+RK+SJ | COMPLETED | 2018-03-11
SB3/US8 | Add Question | SB2/D6/T1 | Designing of GUI | PS | COMPLETED | 2018-03-11
|  | SB2/D6/T2 | Validating user input at client level | PS+RK | COMPLETED | 2018-03-11
|  | SB2/D6/T3 | Validating user input at server level | SJ+RK | COMPLETED | 2018-03-11
|  | SB2/D6/T4 | Connection with Database to insert the record. | SJ | COMPLETED | 2018-03-11
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | PS+RK+SJ | COMPLETED | 2018-03-11

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup |  |  | completed
|  | Search about components required |  |  | completed
|  | Purchase component from Market |  |  | completed
|  | Develop the hardware |  |  | completed
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application |  |  | completed
|  | search paint application |  |  | completed
|  | search video making application |  |  | completed
|  | search audio recording applications |  |  | completed
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials |  |  | completed
|  | Study tutorials |  |  | completed
|  | start with Basics of c# |  |  | completed
|  | start with Basics of c# |  |  | completed
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c# |  |  | completed
|  | start with Basics of c# |  |  | completed
|  | coding of onscreen application |  |  | completed | 0
|  | coding of onscreen application |  |  | completed | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  | completed | 0
|  | coding of onscreen application |  |  | completed | 0
|  | Debug the code |  |  | completed
|  | Debug the code |  |  | completed
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
|  | Implentation of application on virtual screen. |  |  | completed
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen |  |  | completed
|  | Interface it with PC/laptop |  |  | completed
|  | Switch on the projector and set the projected screen |  |  | completed
|  | Interface it with PC/laptop |  |  | completed
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen |  |  | completed
|  | Use different applications on the virtual screen |  |  | completed
|  | Check the changes made at the virtual screen |  |  | completed
|  | Checking if it is working effectively with the laptop and not damaged |  |  | completed
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables |  |  | completed
|  | Prepare all software deliverables |  |  | completed
|  | Prepare a hardware & software guide |  |  | completed
|  | Prepare a user manual & guide for the users |  |  | completed
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project |  |  | completed
|  | Project demonstration |  |  | completed
|  | Project demonstration |  |  | completed
|  | Project to be operated by different users |  |  | completed
| PS | Pankaj Sharma
| RK | Ravi Kumawat
| SJ | Sunil Jangid
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 25 | 25 | Tasks
2018-10-18 | 21 | 25
2018-10-20 | 17 | 25
2018-10-21 | 10 | 25
2018-10-22 | 5 | 25
2018-10-23 | 0 | 25
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 -<Assessment Portal>
SB4/US1 | ADMIN | SB4/D1/T1 | Testing of recommendation system related to admin | PS | COMPLETED | 15-01-2019
|  | SB4/D1/T2 | Testing of whole system application | RK | COMPLETED | 15-01-2019
|  | SB4/D1/T3 | Testing of database related to admin | RK+PS+SJ | COMPLETED | 15-01-2019
SB4/US2 | USER | SB4/D1/T1 | Testing of recommendation system related to user | SJ | COMPLETED | 15-01-2019
|  | SB4/D1/T2 | Testing of whole system application | RK | COMPLETED | 15-01-2019
|  | SB4/D1/T3 | Testing of database related to user | SJ | COMPLETED | 15-01-2019
COMPLETED
[5 empty] | COMPLETED | 20-01-2019
SB4/US3 | DATABASE | SB4/D1/T1 | check the complete database | RK | COMPLETED | 20-01-2019
|  | SB4/D1/T2 | check the query those are used | RK | COMPLETED | 20-01-2019
|  | SB4/D1/T3 | check the table those are in the database | RK+PS+SJ | COMPLETED | 20-01-2019

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup |  |  | not completed
|  | Search about components required |  |  | not completed
|  | Purchase component from Market |  |  | not completed
|  | Develop the hardware |  |  | not completed
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application |  |  | not completed
|  | search paint application |  |  | not completed
|  | search video making application |  |  | not completed
|  | search audio recording applications |  |  | not completed
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials |  |  | not completed
|  | Study tutorials |  |  | not completed
|  | start with Basics of c# |  |  | not completed
|  | start with Basics of c# |  |  | not completed
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c# |  |  | not completed
|  | start with Basics of c# |  |  | not completed
|  | coding of onscreen application |  |  | not completed | 0
|  | coding of onscreen application |  |  | not completed | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  | not completed | 0
|  | coding of onscreen application |  |  | not completed | 0
|  | Debug the code |  |  | not completed
|  | Debug the code |  |  | not completed
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. |  |  | not completed
|  | Implentation of application on virtual screen. |  |  | not completed
|  | Implentation of application on virtual screen. |  |  | not completed
|  | Implentation of application on virtual screen. |  |  | not completed
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen |  |  | not completed
|  | Interface it with PC/laptop |  |  | not completed
|  | Switch on the projector and set the projected screen |  |  | not completed
|  | Interface it with PC/laptop |  |  | not completed
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen |  |  | not completed
|  | Use different applications on the virtual screen |  |  | not completed
|  | Check the changes made at the virtual screen |  |  | not completed
|  | Checking if it is working effectively with the laptop and not damaged |  |  | not completed
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables |  |  | not completed
|  | Prepare all software deliverables |  |  | not completed
|  | Prepare a hardware & software guide |  |  | not completed
|  | Prepare a user manual & guide for the users |  |  | not completed
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project |  |  | not completed
|  | Project demonstration |  |  | not completed
|  | Project demonstration |  |  | not completed
|  | Project to be operated by different users |  |  | not completed
| PS | Pankaj Sharma
| RK | Ravi Kumawat
| SJ | Sunil Jangid
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 10 | 10 | Tasks
2019-01-11 | 7 | 10
2019-01-12 | 5 | 10
2019-01-13 | 3 | 10
2019-01-14 | 1 | 10
2019-01-15 | 0 | 10
0
Days